

FTF FY 2023 Performance Scorecard USAID Ethiopia

This Feed the Future (FTF) Performance Scorecard assesses the USAID Ethiopia progress toward FY 2030 Performance Targets.

# Performance Overview



The FY 2023 **On track** value is determined by drawing a line from the baseline (FY 2022) to the FY 2030 Target. For FY 2023, Performance Targets are considered **On track** if they have reported at least 90% of that value.



**Note:** *For Performance Target 2 (Gender financing ratio), the target is to increase financing to females for those OUs that are already achieving parity ($1).*

*For Performance Target 4 (PSI), all targets are relative to the last three years’ reporting. In future years, the interim targets may increase.*

*For Performance Target 5 (MDD-W), all FY23 actual values are also the baseline, and may have been collected in a prior year. See the detail page for more information.*


*See detailed* [*methodology document*](https://docs.google.com/document/d/13n-43ppFiGKauscQ7HaAiQDCM4DssGEgRdq2fMyTDn0/edit) *here. If you have questions, please email the FTF Data and Analytics team at* [refs.adl.da@usaid.gov](mailto:refs.adl.da@usaid.gov).

### Performance Target (PT) Details

This section shows PT scores for each applicable PT for USAID Ethiopia.

## Performance Target 1: Value of annual sales of producers and firms receiving USG assistance






In FY 2023, USAID Ethiopia had 9 activities that aligned the ‘Value of annual sales from producers and firms receiving USG assistance’ (EG.3.2-26), and 7 contributed to the sales total of $136,800,000.

###### Performance Target 2: Value of financing accessed by female FTF participants per $1 of financing accessed by male FTF participants






In FY 2023, USAID Ethiopia had 6 IMs/Activities that reported all four sex disaggregates needed to contribute to PT2. The total value of financing among all activities, regardless of disaggregates, was $80,110,000 (EG.3.2-27 total), with $80,110,000 that was disaggregated by females and males, and an additional $10,280,000 to ‘mixed’ firms that have both males and females, and $40,000 that was not sex disaggregated.

###### Performance Target 3: Number of cultivated hectares under climate adaptation/climate risk management practices and technologies with USG assistance






In FY 2023, Ethiopia had 24 activities that aligned the indicator for hectares under improved management practices (EG.3.2-25). Of those activities, 3 reported on the ‘Climate adaptation/climate risk management’ disaggregate and contributed to the OU total for this PT.

###### Performance Target 4: Value of private sector investment leveraged by the USG to support food security and nutrition






In FY 2023, Ethiopia had 4 activities that aligned the private sector investment indicator (EG.3.1-15/-14), ‘Value of new private sector investment leveraged by the USG to support food security and nutrition [IM-level]’, and 4 contributed to the OU total in FY 2023.

###### Performance Target 5: Percent of women consuming a diet of minimum diversity (MDD-W)






The baseline population-based survey (PBS) for USAID Ethiopia was in 2018 and showed that 2% of women in the ZOI had access to a minimally-diverse diet. The FY30 target is 5% percent.The most recent PBS was in 2023, but results are not yet available. The following PBS is scheduled for .


### National Context

National level data was collected from the [World Bank’s Open Data portal](https://data.worldbank.org/) that measures key indicators at the national level.




## Agricultural Transformation Index Score

The [IFPRI Agricultural Transformation Index (ATI)](https://agrilinks.org/events/drivers-agrifood-system-transformation-lessons-feed-future-country-studies) Score is a high level indicator of the status of agricultural market systems in each country.



## Budget Trend

At the Operating Unit level, the Performance Targets are based in part on the FY 2024 budget request. The budget chart below includes EG.3 money only.



## Active Portfolio

The following activities are considered “active” based on their reporting in FY 2023 and expected FY 2024 reporting. The Analytics, Data and Learning Division defines an “active” activity as one that reported targets, actuals, or deviation narratives for the current year (FY 2023), or the next out year targets (i.e. FY 2024).

## Top Activities (Award Disbursements and Results)

This section highlights some activities in the USAID Ethiopia (ETHIOPIA) portfolio that have the highest level of disbursements and high reporting values for the relevant indicators. The table below shows the top (up to) five activities by the total transaction amount for disbursements. The columns to the right indicate if these activities are reporting on relevant PT indicators.

| Award Number | Activity Code | Activity Name | FY23 Disbursements | PT1 | PT2 | PT3 | PT4 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 72066320CA00002 | 1778 | Resilience in Pastoral Areas - North | $10,468,759 | X | X | X | X |
| 72066320CA00001 | 1779 | Resilience in Pastoral Areas - South | $9,785,193 | X | - | - | X |
| AID-663-A-17-00001 | 1742 | FtF Ethiopia - Livelihoods for Resilience Activity | $8,528,454 | X | X | - | - |
| 7200AA19C00080 | 4634 | Market Systems for Growth | $5,817,944 | - | X | - | - |

**The next table (below) shows the top reporting activities.**

| Award Number | Activity Code | Activity Name | Total Disbursements | Sales | Hectares | PSI |
| --- | --- | --- | --- | --- | --- | --- |
| 7200AA18CA00008 | 4642 | Feed the Future Ethiopia Alliance for Inclusive and Nutritious Food Processing | $332,904 | $91,584,978 | NA | $4,085,335 |
| 72066320CA00002 | 1778 | Resilience in Pastoral Areas - North | $10,468,759 | $20,600,207 | 42 | $494,722 |
| AID-663-A-17-00001 | 1742 | FtF Ethiopia - Livelihoods for Resilience Activity | $8,528,454 | $18,700,880 | NA | NA |
| 72066320CA00001 | 1779 | Resilience in Pastoral Areas - South | $9,785,193 | $2,931,328 | NA | $6,051,661 |
| 720BHA21CA00036 | 4904 | Resilience Food Security Activity (RFSA)-WV | NA | $2,024,235 | 1 640 | NA |

### Appendix 1: Response to “Not on track” Performance Targets

This section provides space for USAID Ethiopia to provide an explanation of why the following PTs are not on track and how you could adjust to be on track in the coming year(s). To help in your response(s), the relevant section of the FTF/GFS Key Issue Narrative (KIN) is provided, as it *may be* useful in drafting a responses. Note that the KIN is addressing the sum of the out year targets (FY 2023) set by the USAID Ethiopia activities that are reporting on each PT. The FY 2023 out year targets were set prior to the establishment of the FY 2030 Performance Targets, so the below explanations from the KIN may not apply to the Performance Target deviation.

* In Section 4 of the FTF KIN, your OU discusses FY24 and FY25 targets, while these Scorecards are addressing progress against a trajectory from historical reporting to your OU’s FY30 target.  Also, the FY 2023 out year targets were set prior to the establishment of the FY 2030 Performance Targets.  Therefore, the below explanations from the KIN may not apply to these FY30 Performance Target deviations.
* These responses will be used to compile a Congressional report, the GFSS Implementation Report, to discuss progress against the FTF FY 2030 Performance Targets, as mandated by the GAO.
* Only PTs that are ‘Not on Track’ require review and explanation from the OU.

## Performance Target 2: Gender financing ratio

*Excerpt from FY23 KIN Section 4 to consider:* Ethiopia, the gender gap in accessing economic resources such as finance remains a challenge, and this has been counterproductive in improving household welfare. Despite huge room for improvement, USAID/Ethiopia has been working to close the gender disparity in financial access between male and female proprietors via a number of activities which targeted women-owned businesses and small-enterprises. In FY2023, the total amount of cash debt and non-debt finance received by female producers/proprietors was $13,626,363.00, whereas the value for male counterparts was $70,660,524.00. The performance of Value of finance accessed by females per dollar of finance accessed by males was 0.19 showing that for every one dollar accessed by men, women were having sixteen cents that demonstrate huge gender gap and unmet demand by females. The mission is working to address this gap through tailored grant provision to women, engaging women in the value chain development interventions, enabling women to access land and encouraging them to collateralize their land to financial institutions etc.

#### Enter USAID Ethiopia (ETHIOPIA) Response Below:

## Performance Target 3: Hectares under climate adaptive and risk management practices

*Excerpt from FY23 KIN Section 4 to consider:* /A

#### Enter USAID Ethiopia (ETHIOPIA) Response Below: