
FTF FY 2023 Performance Scorecard West Africa Regional Program

This Feed the Future (FTF) Performance Scorecard assesses the West Africa Regional Program progress toward FY 2030 Performance Targets.

# Performance Overview



The FY 2023 **On track** value is determined by drawing a line from the baseline (FY 2022) to the FY 2030 Target. For FY 2023, Performance Targets are considered **On track** if they have reported at least 90% of that value.



**Note:** *For Performance Target 2 (Gender financing ratio), the target is to increase financing to females for those OUs that are already achieving parity ($1).*

*For Performance Target 4 (PSI), all targets are relative to the last three years’ reporting. In future years, the interim targets may increase.*

*For Performance Target 5 (MDD-W), all FY23 actual values are also the baseline, and may have been collected in a prior year. See the detail page for more information.*


*See detailed* [*methodology document*](https://docs.google.com/document/d/13n-43ppFiGKauscQ7HaAiQDCM4DssGEgRdq2fMyTDn0/edit) *here. If you have questions, please email the FTF Data and Analytics team at* [refs.adl.da@usaid.gov](mailto:refs.adl.da@usaid.gov).

### Performance Target (PT) Details

This section shows PT scores for each applicable PT for West Africa Regional Program.

## Performance Target 1: Value of annual sales of producers and firms receiving USG assistance






In FY 2023, USAID West Africa Regional Program had 1 activities that aligned the ‘Value of annual sales from producers and firms receiving USG assistance’ (EG.3.2-26), and 1 contributed to the sales total of $72,020,000.

###### Performance Target 2: Value of financing accessed by female FTF participants per $1 of financing accessed by male FTF participants





In FY 2023, USAID West Africa Regional Program had 0 IMs/Activities that reported all four sex disaggregates needed to contribute to PT2. The total value of financing among all activities, regardless of disaggregates, was $170,000 (EG.3.2-27 total), with $170,000 that was disaggregated by females and males, and an additional $42,180,000 to ‘mixed’ firms that have both males and females, and $0 that was not sex disaggregated.

###### Performance Target 3: Number of cultivated hectares under climate adaptation/climate risk management practices and technologies with USG assistance






USAID West Africa Regional Program did not have a PT3 target.

###### Performance Target 4: Value of private sector investment leveraged by the USG to support food security and nutrition





In FY 2023, West Africa Regional Program had 3 activities that aligned the private sector investment indicator (EG.3.1-15/-14), ‘Value of new private sector investment leveraged by the USG to support food security and nutrition [IM-level]’, and 3 contributed to the OU total in FY 2023.

###### Performance Target 5: Percent of women consuming a diet of minimum diversity (MDD-W)





PT5 is not available for USAID West Africa Regional Program.

### National Context

National context data is not available for West Africa Regional Program.

## NULL


## Agricultural Transformation Index Score

The [IFPRI Agricultural Transformation Index (ATI)](https://agrilinks.org/events/drivers-agrifood-system-transformation-lessons-feed-future-country-studies) Score is a high level indicator of the status of agricultural market systems in each country.

## [1] "No Ag Transformation Index available for West Africa Regional Program."

## Budget Trend

At the Operating Unit level, the Performance Targets are based in part on the FY 2024 budget request. The budget chart below includes EG.3 money only.



## Active Portfolio

The following activities are considered “active” based on their reporting in FY 2023 and expected FY 2024 reporting. The Analytics, Data and Learning Division defines an “active” activity as one that reported targets, actuals, or deviation narratives for the current year (FY 2023), or the next out year targets (i.e. FY 2024).

## Top Activities (Award Disbursements and Results)

This section highlights some activities in the West Africa Regional Program (WARP) portfolio that have the highest level of disbursements and high reporting values for the relevant indicators. The table below shows the top (up to) five activities by the total transaction amount for disbursements. The columns to the right indicate if these activities are reporting on relevant PT indicators.

| Award Number | Activity Code | Activity Name | FY23 Disbursements | PT1 | PT2 | PT3 | PT4 |
| --- | --- | --- | --- | --- | --- | --- | --- |

**The next table (below) shows the top reporting activities.**

| Award Number | Activity Code | Activity Name | Total Disbursements | Sales | Hectares | PSI |
| --- | --- | --- | --- | --- | --- | --- |
| 72062019C00003 | 2204 | West Africa Trade and Investment Hub (WATIH) - (West Africa Regional OU) | NA | $72,018,184 | NA | $42,172,381 |
| 72062422IO00002 | 1824 | 109653: SERVIR West Africa (SERVIR WA 2) | NA | NA | 5 298 | NA |
| AID-624-A-16-00010 | 1825 | 103958: Sustainable Shea Initiative | NA | NA | NA | $1,598,205 |
| 72062418IO00001 | 1819 | 103959: Enhancing Growth through Regional Agricultural Input Systems (EnGRAIS) | NA | NA | NA | $3,780,000 |
| AID-624-A-17-00002 | 1822 | 101303: Partnership for Agricultural Research, Education and Development (PAIRED) in West Africa | NA | NA | NA | NA |

### Appendix 1: Response to “Not on track” Performance Targets

This section provides space for West Africa Regional Program to provide an explanation of why the following PTs are not on track and how you could adjust to be on track in the coming year(s). To help in your response(s), the relevant section of the FTF/GFS Key Issue Narrative (KIN) is provided, as it *may be* useful in drafting a responses. Note that the KIN is addressing the sum of the out year targets (FY 2023) set by the West Africa Regional Program activities that are reporting on each PT. The FY 2023 out year targets were set prior to the establishment of the FY 2030 Performance Targets, so the below explanations from the KIN may not apply to the Performance Target deviation.

* In Section 4 of the FTF KIN, your OU discusses FY24 and FY25 targets, while these Scorecards are addressing progress against a trajectory from historical reporting to your OU’s FY30 target.  Also, the FY 2023 out year targets were set prior to the establishment of the FY 2030 Performance Targets.  Therefore, the below explanations from the KIN may not apply to these FY30 Performance Target deviations.
* These responses will be used to compile a Congressional report, the GFSS Implementation Report, to discuss progress against the FTF FY 2030 Performance Targets, as mandated by the GAO.
* Only PTs that are ‘Not on Track’ require review and explanation from the OU.

## Performance Target 2: Gender financing ratio

*Excerpt from FY23 KIN Section 4 to consider:* FY2023, USAID/West Africa aimed to provide $143,319 in finance to female program participants but exceeded this target by achieving $168,593.22 in finance accessed by these participants. This success was attributed to the improved ability of female cooperatives to engage with formal financial institutions. Throughout the reporting year, the cooperatives benefited from training and technical assistance provided by the FtF-supported project Sustainable Shea Intensification (SSI), resulting in better formalized structures. This enabled them to establish relationships with various formal financial institutions and secure more pre-financing for their work, particularly in shea aggregation. For FY2024, the Regional mission is targeting $15,000 in finance to be accessed by women participants. This lower target is due to the end of the Activity in June 2024.

#### Enter West Africa Regional Program (WARP) Response Below: